## Look-Ahead
BART CBTC — Weekly Look-Ahead
# | Activity ID | Description of Work Activity | Location | SSWP# | Resource | Work Hours | Week 21 | [6 empty] | Week 22
[7 empty] | May 18 – May 24 | [6 empty] | May 25 – May 31
May
[7 empty] | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
1 | AT-LM-001 | CBTC Onboard Equipment Functional Test | LMA Yard | SSWP-014 | AK, JS | 0700-1500 | bar: May 18 Mon to May 19 Tue
2 | AT-LM-002 | Wayside Radio Coverage Verification | Embarcadero | SSWP-021 | JS, RM | 2000-0700 | bar: May 20 Wed to May 21 Thu
3 | AT-LM-003 | Track Circuit Continuity Sweep | Powell | SSWP-018 | AK | bar: May 22 Fri
4 | AT-LM-004 | ATP Brake Curve Validation (CANCELLED) | Daly City | SSWP-009 | RM, JS | 0700-1500 | bar: May 23 Sat
5 | AT-LM-005 | Interlocking Logic Acceptance | Bay Fair | SSWP-007 | AK, RM | 0700-1500 | bar: May 25 Mon to May 27 Wed
6 | AT-LM-006 | Penalty Brake Application Test | 24th Street | SSWP-011 | JS | 0800-1600 | bar: May 28 Thu
7 | AT-LM-007 | Cab Signal Receiver Verification | Coliseum | SSWP-022 | AK, JS | 2100-0500 | bar: May 29 Fri to May 30 Sat
8 | AT-LM-008 | Subsystem Integration Smoke Test | OAK Wye | SSWP-025 | bar: May 31 Sun
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23

## Instructions
Lookahead Import Template
Sheet name | Must be exactly "Look-Ahead" (case-insensitive substring match).
Main header row | Row 2: Activity ID (B), Description of Work Activity (C), Location (D), SSWP# (E), Resource (F, comma-separated initials), Work Hours (G).
Date header rows | Rows 2–6 hold week #, week label, month, day number, weekday. The importer reads Month (row 4) and Day (row 5).
Data rows | Start at row 7. Empty rows are skipped automatically.
Hidden columns | Historical columns can be hidden — the importer ignores them.
Resource initials | Use a comma, slash, or semicolon separator (AK, JS or AK/JS). Unknown initials land in the admin Review Queue after import.
Work hours format | Accepts 0700-1500, 0700 - 1500, 2000-0700 (overnight), 7:00-15:00, 8am-4pm. If the cell is blank, the shift color picks the default time band.
Cell color coding | Fill the day cell for each scheduled activity with one of these colors:
Yellow | Day shift — default 07:00–15:00 (overridden by Work Hours when present)
Blue | Night shift — default 20:00–07:00 (overridden by Work Hours when present)
Black | Blanket shift — all-day, no specific time window
Red | Cancelled — event is recorded as cancelled. Admin must add a cancellation reason from the Review Queue after import.
Matching engine | Each row is matched to a portal activity in priority order: (1) exact Activity ID against test_items.TestCaseCode/TestID, (2) P6 activity → p6_activity_map → test case code, (3) normalized description, (4) Fuse.js fuzzy match on description + location. Unmatched rows still import — admin can link them later from the Review Queue.
Supersede behavior | On confirm, the new file replaces any future-dated events from the previous batch. Events marked Locked from the Event Detail Modal are preserved across imports.
Tips | • Tolerate slight color shade variation — the importer matches by RGB distance. • You can hide any prior-week columns; they will be ignored. • Sample data on the Look-Ahead sheet demonstrates each color and work-hour pattern.